## Main page
No. | Risk Category (First level) | Sub Category (Second Level) | Risk Factors (Third Level) | Risk Code
A | Geological characteristic | 1. Type of rock present | Hard rock present across alignment of tunnel | T1
|  |  | Soft rock present across alignment of tunnel | T2
|  |  | Fractured rock present across alignment of tunnel | T3
|  |  | Frequent settlement of ground | T4
|  |  | Presence of water-soluble rock beneath tunnel | T5
|  |  | Contaminated ground conditions | T6
|  | 2. Poor geotechnical survey | Large amount of Subsurface erosion | T7
|  |  | Presence of fault, discontinuities and fissures in tunnel alignment | T8
|  |  | Not reliable regional geological information | T9
|  |  | Not able to predict ground strata correctly | T10
|  |  | Unstable ground or unanticipated ground behaviour | T11
|  |  | Surprise Soil condition during construction | T12
B | Site Condition | 3. Limited response capability due to confined working environment | On Site unanticipated obstructions, natural or manmade. | T13
|  |  | Unassured supply of basic facilities like electricity and mechanical work | T14
|  |  | Inappropriate access to site locatio | T15
|  | 4. Poor surface investigation prior to work | Delays in transferring of construction site to contractor from owner to start work. | T16
|  |  | Insufficient number of bore holes to predict general nature of rock mass | T17
C | Groundwater | 5. Excessive ground water inflow | Presence of water source near tunnel construction site. | T18
|  |  | Erosion of soil inside tunnel due to high groundwater flow | T19
|  | 6. Extra Dewatering work | Misinterpretation of soil and groundwater conditions leading to the choice of an inappropriate construction methods or equipment. | T20
|  |  | Presence of ground water table close to tunnel bottom | T21
D | Actual construction | 7. Scheduling not following as per planning | Unavailability of required resources like man, equipment and materials. | T22
|  |  | Poor Quality of construction | T23
|  | 8. Selection of an Inappropriate construction methods | Inadequate provision of grouting | T24
|  |  | Tunnel lining not done properly | T25
|  |  | Fault in maintaining tunnel alignment | T26
|  |  | Work quality not accepted by client | T27
|  | 9. Poor safety precautions during construction | Inappropriate measures of waste [muck extract from tunnel] disposal | T28
|  |  | Not having mechanised and automatic tunnel drive by TBM | T29
|  |  | Groundwater leakages in tunnel after completion | T30
|  |  | Unstable tunnel walls and roof after construction | T31
E | Administration | 10. Delay in sanctioning various permits for tunnel construction from authorities | Problem with land acquisition | T32
|  |  | Problem of human resource coordination for their increment, demands, training etc | T33
|  |  | Dividing complete tunnelling work in several sub-contractor | T34
|  |  | Problem with funds availability | T35
|  |  | Lack of experience in executing tunnelling work | T36
F | Design | 11. Technical error in Design | Poor Judgement in design | T37
|  |  | Incompatible Construction Method Selection misinterpretation of site information provided by owner. | T38
|  |  | Not sharing 100 percent correct site information to design team | T39
|  | 12. Delays in design changes | Modification of design during construction. | T40
|  |  | Incomplete plans provided to design department from planning | T41
G | Management | 13. Top Management Policies and Decision | Poor communication of instructions | T42
|  |  | Inappropriate construction planning | T43
|  |  | Conflict among project participant | T44
|  |  | Lack of funding in case of new problem arises | T45
|  | 14. Project Manager competence | Failure in commitment by parties in contract that are Owner and Contractor | T46
|  |  | Inadequate safety policies | T47
H | Faults in contracting | 15. Site Conditions not as predicted in contract | Behaviour of soil and groundwater different from that ordinarily expected or compared to conditions presented in the contract | T48
|  |  | Variation in construction material prices | T49
|  | 16. Changes in legislation, policies and regulations | Changes in work scope stated in contract delay in dispute resolution | T50
I | Resource Monitoring | 17. Failure of TBM | Selection of unsuitable TBM for strata given | T51
|  |  | Mobilisation of TBM assembly | T52
|  |  | Unavailability of TBM spare part on time due to lack of supply by manufacturer | T53
|  | 18. Maintenance of equipment | Adverse environmental working conditions | T54
|  |  | Damage to other vicinity structures | T55
|  |  | Frequent breakdown of TBM machine | T56
J | Miscellaneous | 19. Act of God | Unexpected major calamities like earthquake. landslide, volcanic eruption etc. | T57

## Summary
No. | Risk Category (First level) | Sub Category (Second Level) | Risk Factors (Third Level) | Risk Code
A | Geological characteristics | 1. Type of rock present | Hard rock present across alignment of tunnel | T1
|  |  | Soft rock present across alignment of tunnel | T2
|  |  | Fractured rock present across alignment of tunnel | T3
|  |  | Frequent settlement of ground | T4
|  |  | Presence of water-soluble rock beneath tunnel | T5
|  |  | Contaminated ground conditions | T6
|  | 2. Poor geotechnical survey | * | *
|  |  | * | *
B | Site Condition | * | * | *
|  | * | * | *
C | Groundwater | * | * | *
|  | * | * | *
|  | * | * | *
J | Miscellaneous | 19. Act of God | Unexpected major calamities like earthquake. landslide, volcanic eruption etc. | T57

## Experimentation results
expert | Result 1 |  | Result 2 |  | Result 3
[5 empty] | Risk category | Sub category risk | Risk factor
| Project type | Main category | Risk category | Sub category risk | Design Risk | Technical error in Design | Poor Judgement in design
| Tunnel | Geological characteristic | Design Risk | Technical error in Design |  |  | Incompatible Construction Method Selection misinterpretation of site information provided by owner.
|  | Site Condition |  | Delays in design changes |  |  | Not sharing 100 percent correct site information to design team
|  | Groundwater |  |  |  | Delays in design changes | Modification of design during construction.
|  | Actual construction |  |  |  |  | Incomplete plans provided to design department from planning
Administration
Design
Management
Faults in contracting
Resource Monitoring
Miscellaneous